## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Smart UAV Framework for Multi-Assistance |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P SHAH INSTITUE OF TECHNOLOGY, IT
PROJECT GUIDE |  | PROF. VISHAL BADGUJAR |  |  |  |  | DATE | [6 empty] | 2021-05-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Vaishnavi,Vaishnavi,Utkarsha | 2020-01-20 | 2020-02-08 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Vaishnavi,Vaishnavi,Utkarsha | 2020-02-08 | 2020-02-26 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Vaishnavi,Vaishnavi,Utkarsha | 2020-02-28 | 2020-03-14 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Utkarsha | 2020-03-14 | 2020-03-20 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Vaishnavi Potphode | 2020-03-21 | 2020-03-27 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Vaishnavi, Utkarsha | 2020-03-28 | 2020-04-03 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Vaisnavi Patil | 2020-03-04 | 2020-03-12 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | Utkarsha | 2020-03-04 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Vaishnavi | 2020-03-04 | 2020-03-06 | 1 | 100% | bar: WEEK 3 F
1.9 | Benefits for environment | Vaishnavi Potphode | 2020-03-06 | 2020-03-07 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Utkarsha | 2020-03-07 | 2020-03-08 | 1 | 100% | bar: WEEK 3 F
1.11 | Applications | Vaishnavi Patil | 2020-03-07 | 2020-03-08 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Exsiting System | Vaishnavi,Vaishnavi,Utkarsha | 2020-09-21 | 2020-10-06 | 2 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Proposed System | Vaishnavi,Vaishnavi,Utkarsha | 2020-09-21 | 2020-10-06 | 2 | 100% | bar: WEEK 4 F to WEEK 5 F
3 | Project Implementation
3.1 | Counting & Announcement | Utkarsha, Vaishnavi Potphode | 2021-02-04 | 2021-02-06 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
3.2 | Tracking Social Distance | Vaishnavi Potphode | 2021-03-02 | 2021-03-08 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
3.3 | Storing | Vaishnavi, Vaishnavi | 2021-03-10 | 2021-03-16 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
3.4 | Monitoring | Utkarsha,Vaishhnavi Patil | 2021-03-20 | 2021-04-02 | 2 | 100% | bar: WEEK 6 M to WEEK 6 F
3.5 | Tinkercad Design | Vaishnavi Potphode | 2021-03-20 | 2021-03-20 | 0 | 100% | bar: WEEK 6 M to WEEK 6 F
4 | Testing
4.1 | Code Testing | Vaishnavi,Vaishnavi,Utkarsha | 2021-04-03 | 2021-04-04 | 1 | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 7 M
4.2 | Drone Simulation | Vaishnavi,Vaishnavi,Utkarsha | 2021-04-11 | 2021-04-11 | 0 | 100% | bar: WEEK 7 M
5 | Results and Analysis
5.1 | Analysing the Output | Vaishnavi, Vaishnavi | 2021-04-12 | 2021-04-14 | 1 | 100% | bar: WEEK 7 M
5.2 | Storing the Output | Vaishnavi, Vaishnavi | 2021-04-14 | 2021-04-17 | 1 | 100% | bar: WEEK 7 M
5.3 | Accessing the monitored video | Vaishnavi Patil, Utkarsha | 2021-04-14 | 2021-04-17 | 1 | 100% | bar: WEEK 7 M
6 | Conclusion
6.1 | Report Preparation and Documentation | Vaishnavi, Vaishnavi, Utkarsha | 2021-04-30 | 2021-05-07 | 1 | 100% | bar: WEEK 7 M